## Sheet1
LED String Animation Project Plan [PO5_LSAN] |  |  | Team Lead: Youssef Kamal |  |  |  | Members: | Waleed Adel - Sara Abd ElRahman - Mennatullah Mostafa - Mohanad Sallam
Task | Description | ID | Assigned to | Assignation Date | Actual Start Date | Dead Line | Estimate Time | Actual Delivery Date | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Comments
CYRS_TASK001_V1 | Make Template to the CYRS document | TASK001 | Menna | 2020-01-21 | 2020-01-23 | 2020-01-23 | 1h | 23/1/2020 | Revised
SRS_TASK002_V1 | Make Template to the SRS document | TASK002 | Mohanad | 2020-01-21 | 22/1/2020 | 23/01/2020 | 24h | 23/1/2020 | Revised
HSI_TASK003_V1 | Make Template to the HSI document | TASK003 | Waleed | 2020-01-21 | 22/1/2020 | 23/1/2020 | 24h | 23/1/2020 | Revised
SIQ_TASK004_V1 | Make Template to the SIQ document | TASK004 | Sara | 2020-01-21 | 2020-01-22 | 2020-01-24 | 48 h | 23/1/2020 | Revised
CYRS_TO_SRS_TASK005_V1 | Break down Software requirments from CYRS to SRS requirments | TASK005 | Mohanad and Sara | 24/1/2020 | 28/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised
CYRS_TO_HSI_TASK006_V1 | Break down Hardware requirments from CYRS to HSI requirments | TASK006 | Walid and Menna | 24/1/2020 | 28/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised
REV_TO_CYRS_TASK007_V1 | Do the changes required in the review sheet to CYRS document | TASK007 | Menna | 25/1/2020 | 28/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised
SIQ_Repair_TASK008_V1 | Remove questions asked by developer to developer. | TASK008 | Sara | 2020-03-02 | 2020-02-02 | 2020-04-02 | 24h | 2020-03-02 | Revised
CRS_ADD_ID_TASK009_V1 | Add ID to all three requirments in CRS requirments so we can track them in CYRS and HIS | TASK009 | Walid | 2020-03-02 | 2020-03-02 | 2020-04-02 | 24h | 2020-04-02 | Revised | [7 empty] | Pushhed on 4/2 but done on 3/2 and had been commited
MAKE_CLEAR_CRS_TASK010_V1 | Ask the costmer all the questiones that are mentioned in the meeting using the SIQ board (Can we use tri state flip switch in TI switch?, be more specefic in the welcome mode and the TI states, etc….) | TASK010 | Sara | 2020-03-02 | 2020-02-02 | 2020-04-02 | 24h | 2020-03-02 | Revised
MAKE_DESCRIPTION_TASK011_V1 | Make a good description to CYRS, HSI and SRS and use the same block diagram from HIS in all of them. Also remove all unused tiles like features in HIS. Also remove | TASK011 | Mohanad | 2020-03-02 | 2020-03-02 | 2020-04-02 | 24h | 2020-04-02 | Revised
CYRS_BREAKDOWN_TASK012_V1 | Break Down CRS to more than one CYRS requirment with more clear requirments. Also use the costmer answers from SIQ sheet. Also use the CRS requirment ID to track down the origin of each CYRS requirment. Also fix the versions in the history table. | TASK012 | Menna | 2020-04-02 | 2020-05-02 | 2020-06-02 | 48h | 2020-06-02 | Revised
HSI_ADD_REQ_ID_TASK013_V1 | Add ID to each HIS component. Also mention The ID from CRS that this component covers. Also add description to Hardware if needed. | TASK013 | Walid | 2020-04-02 | 2020-04-02 | 2020-05-02 | 24h | 2020-05-02 | Revised
SRS_REFORM_TASK014_V1 | Reforme SRS to match the new CYRS (Released). NB: Two Branches hase to be created by Team leader. | TASK014 | Sara and Mohanad | 2020-07-02 |  | 2020-08-02 | 24h | 2020-07-02 | Revised
SIQ_AKNOWLAGE_TASK015_V1 | Read the new answers in the SIQ and aknowlage them | TASK015 | Sara | 2020-04-02 | 2020-04-02 | 2020-04-02 | 12h | 2020-04-02 | Revised
HSI_COVER_SIQ_TASK016_V1 | Cover all uncovered SIQ in HIS | TASK016 | Walid | 2020-05-02 | 2020-05-02 | 2020-07-02 | 12h | 2020-07-02 | Revised
BLOCK_DIAG_UPDATE_TASK017_V1 | Update CYRS and SRS with the block diagram from HIS document. This task should be done after finishing the SRS rightaway. | TASK017 | Sara | 2020-07-02 |  | 2020-07-02 | 12h | 2020-07-02 | Asseigned
CYRS_6AND7_CHANGE_TASK018_V1 | Change CYRS to follow the review sheet | TASK018 | Menna | 2020-07-02 | 2020-07-02 | 2020-07-02 | 12h | 2020-07-02 | Revised
UPDATE_SRS_TASK019_V1 | Update SRS according to CYRS 6 and 7 | TASK019 | Mohanad | 2020-07-02 | 2020-07-02 | 2020-07-02 | 12h | 2020-07-02 | Revised
REARRANGE_CYRS_TASK020_V1 | Update CYRS arrangment so than status and document history before table of content. Also change the colour of the ID | TASK020 | Menna | 2020-08-02 | 2020-08-02 | 2020-08-02 | 12h |  | Asseigned
HIS_TASK21_V1 | Update HIS with all the points mentioned in lecture | TASK021 | Walid | 2020-08-02 | 2020-08-02 | 2020-08-02 | 12h |  | Asseigned
|  | TASK022 | [6 empty] | Asseigned
|  | TASK023 | [6 empty] | Asseigned
|  | TASK024 | [6 empty] | Asseigned
|  | TASK025 | [6 empty] | Asseigned
|  | TASK026 | [6 empty] | Asseigned
|  | TASK027 | [6 empty] | Asseigned
|  | TASK028 | [6 empty] | Asseigned
|  | TASK029 | [6 empty] | Asseigned
|  | TASK030 | [6 empty] | Asseigned
|  | TASK031 | [6 empty] | Asseigned
|  | TASK032 | [6 empty] | Asseigned
|  | TASK033 | [6 empty] | Asseigned
|  | TASK034 | [6 empty] | Asseigned
|  | TASK035 | [6 empty] | Asseigned
|  | TASK036 | [6 empty] | Asseigned
|  | TASK037 | [6 empty] | Asseigned
|  | TASK038 | [6 empty] | Asseigned
|  | TASK039 | [6 empty] | Asseigned
|  | TASK040 | [6 empty] | Asseigned
|  | TASK041 | [6 empty] | Asseigned
|  | TASK042 | [6 empty] | Asseigned
|  | TASK043 | [6 empty] | Asseigned
|  | TASK044 | [6 empty] | Asseigned
|  | TASK045 | [6 empty] | Asseigned
|  | TASK046 | [6 empty] | Asseigned
|  | TASK047 | [6 empty] | Asseigned
|  | TASK048 | [6 empty] | Asseigned
|  | TASK049 | [6 empty] | Asseigned
|  | TASK050 | [6 empty] | Asseigned
|  | TASK051 | [6 empty] | Asseigned
|  | TASK052 | [6 empty] | Asseigned
|  | TASK053 | [6 empty] | Asseigned
|  | TASK054 | [6 empty] | Asseigned
|  | TASK055 | [6 empty] | Asseigned
|  | TASK056 | [6 empty] | Asseigned
|  | TASK057 | [6 empty] | Asseigned
TASK058