## Sheet1
LED String Animation Project Plan [PO5_LSAN] |  |  | Team Lead: Youssef Kamal |  |  |  | Members: | Waleed Adel - Sara Abd ElRahman - Mennatullah Mostafa - Mohanad Sallam
Task | Discription | ID | Assigned to | Assignation Date | Actual Start Date | Estimate Delivery Date | Estimate Time | Actual Delivery Date | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7
CYRS_TASK001_V1 | Make Template to the CYRS document | TASK001 | Menna | 2020-01-21 | 2020-01-23 | 2020-01-23 | 1h | 23/1/2020 | Revised
SRS_TASK002_V1 | Make Template to the SRS document | TASK002 | Mohanad | 2020-01-21 | 22/1/2020 | 23/01/2020 | 24h | 23/1/2020 | Revised
HSI_TASK003_V1 | Make Template to the HSI document | TASK003 | Waleed | 2020-01-21 | 22/1/2020 | 23/1/2020 | 24h | 23/1/2020 | Revised
SIQ_TASK004_V1 | Make Template to the SIQ document | TASK004 | Sara | 2020-01-21 | 2020-01-22 | 2020-01-24 | 48 h | 23/1/2020 | Revised
CYRS_TO_SRS_TASK005_V1 | Break down Software requirments from CYRS to SRS requirments | TASK005 | Mohanad and Sara | 24/1/2020 | 29/1/2020 | 30/1/2020 | 24h |  | In progress
CYRS_TO_HSI_TASK006_V1 | Break down Hardware requirments from CYRS to HIS requirments | TASK006 | Walid and Menna | 24/1/2020 | 29/1/2020 | 30/1/2020 | 24h |  | In progress
REV_TO_CYRS_TASK007_V1 | Do the changes required in the review sheet to CYRS document | TASK007 | Menna | 25/1/2020 | 29/1/2020 | 30/1/2020 | 24h |  | In progress
TASK008
TASK009
TASK010
TASK011
TASK012
TASK013
TASK014
TASK015
TASK016
TASK017
TASK018
TASK019