## Sheet1
LED Stringn Animation Project Plan [PO5_LSAN] |  |  | Team Lead: Youssef Kamal |  |  |  | Members: | Waleed Adel - Sara Abd ElRahman - Mennatullah Mostafa - Mohanad Sallam
Task | Discription | ID | Assigned to | Assignation Date | Actual Start Date | Estimate Delivery Date | Estimate Time | Actual Delivery Date | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7
CYRS_TASK001_V1 | Make Template to the CYRS document | TASK001 | Menna | 2020-01-21 |  |  |  |  | Asseigned
SRS_TASK002_V1 | Make Template to the SRS document | TASK002 | Mohanad | 2020-01-21 |  |  |  |  | Asseigned
HSI_TASK003_V1 | Make Template to the HSI document | TASK003 | Waleed | 2020-01-21 | 22/1/2020 | 23/1/2020 | 24h |  | In progress
SIQ_TASK004_V1 | Make Template to the SIQ document | TASK004 | Sara | 2020-01-21 | 2020-01-22 | 2020-01-24 | 48 h |  | In progress
TASK005
TASK006
TASK007
TASK008
TASK009
TASK010
TASK011
TASK012
TASK013
TASK014
TASK015
TASK016
TASK017
TASK018
TASK019