## HSI review
Date | Reviewer | Review point | Acceptance | Point status | Comment
2020-06-02 | Ali | Remove Team names (under project name) | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Update status to proposed as SRS is under review now | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Please provide a reference table to have "Doc. No, Ref. Doc. Name, Ref. doc. Status". |  | Closed | Mali 13/2/2020: Point still open
2020-06-02 | Ali | Remove references section | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Remove system features section | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | For every requirement, please provide a tacle like the one in presentation | Accepted | Closed | Mali 13/2/2020: Point is closed
13/2/2020 | Ali | From requirement SRS_003 till SRS_010: Under which conditions this sequence will be applied you should declare that this requirement is valid if it's mode 1 , shall the developer implement this requirement without knowing the condition to apply this animation or this animation will be applied without any entry condition! The CYRS requirement is clear and saying that if the switch is high SW shall apply mode 1. please make the requirement clear how these requirements has not input !!! the input indeed is mode value (mode 1 or mode 2). Also all these requirements shall be combined in one requirement as they represet the implementation of startup animation mode 1 |  | Closed
13/2/2020 | Ali | Requirement SRS_011: Under which conditions this sequence will be applied you should declare that this requirement is valid if it's mode 2. |  | Closed
13/2/2020 | Ali | Remove status and history from the first page, first page shall be the cover for the doc. |  | Closed