## Review
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2020 | Ali | There are no questions in the SIQ sheet | Accepted | Closed | Mali 30/1/2020: SIQ sheet ptovided with questions
24/1/2020 | Ali | Project name shall be in the middle of first page not the table of contents | Accepted | Open | Mali 25/1/2020: Please remove "1.Project Name" no need for it
24/1/2020 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | Block diagram isn't correct, it shall be a block has input signals(Tail signal - right TI signal - left TI signal - Mode signal) and has outputs (LEDs) |  | Open | Mali 30/1/2020: Please provide a block "Microcontroller" has input side(Input switches) and output side (LEDs)
24/1/2022 | Ali | Requirements section name is wrong, if you are reusing from another project please rename the section to be the name of our project LED string not speed control xD, any way this section's name shall be "Requirements description" | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | Requirements are taken copy paste from CRS please provide the requirements with more details. Ex: Req_LED STRING ANIMATION_PO5_CYRS _ 001: describes the startup animation modes but at startup what will decide the running mode ? You should write a description of the signal/switch that decides the mode to be run, if you will implement this requirement you will run which mode? you will find your self asking about "what does make animation mode is mode 1 not 2?" |  | Open
24/1/2023 | Ali | Req _ LED STRING ANIMATION_PO5_CYRS _ 002 _ v01: Tail LEDs will be ON if Tail switch is ON and will be OFF if Tail switch is OFF But in CYRS the described is that Tail LEDs will be ON whatever Tail switch is ON/OFF | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2024 | Ali | Req _ LED STRING ANIMATION_PO5_CYRS _ 003 _ v01 : Same note as previous point | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2025 | Ali | Requirements IDs shall have a diferent font different color and also version of the requirement shall be "-V01" not "_v01" | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2026 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
30/1/2020 | Ali | Please provide all titles, tables and data with the same format of HSI also the requirement ID with a diff. suitable color |  | Open
30/1/2020 | Ali | Please remove curly brackets | Accepted | Closed | Mali 6/2/2020: Point is reviewed and closed
30/1/2020 | Ali | Edit the affected requirements by SIQ sheet |  | Open

## HSI review
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2026 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed