## Review
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2020 | Ali | There are no questions in the SIQ sheet | Accepted | Closed | Mali 30/1/2020: SIQ sheet ptovided with questions
24/1/2020 | Ali | Project name shall be in the middle of first page not the table of contents | Accepted | Closed | Mali 25/1/2020: Please remove "1.Project Name" no need for it Mali6/2/2020: Point is reviewed and closed
24/1/2020 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | Block diagram isn't correct, it shall be a block has input signals(Tail signal - right TI signal - left TI signal - Mode signal) and has outputs (LEDs) | Accepted | Closed | Mali 30/1/2020: Please provide a block "Microcontroller" has input side(Input switches) and output side (LEDs) Mali 6/2/2020: TI switch still a 3 phase switch while TI has 2 separate switches Mali 9/2/2020: Point is closed
24/1/2022 | Ali | Requirements section name is wrong, if you are reusing from another project please rename the section to be the name of our project LED string not speed control xD, any way this section's name shall be "Requirements description" | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | Requirements are taken copy paste from CRS please provide the requirements with more details. Ex: Req_LED STRING ANIMATION_PO5_CYRS _ 001: describes the startup animation modes but at startup what will decide the running mode ? You should write a description of the signal/switch that decides the mode to be run, if you will implement this requirement you will run which mode? you will find your self asking about "what does make animation mode is mode 1 not 2?" | Accepted | Closed | Mali 6/2/2020: Point is reviewed and closed
24/1/2023 | Ali | Req _ LED STRING ANIMATION_PO5_CYRS _ 002 _ v01: Tail LEDs will be ON if Tail switch is ON and will be OFF if Tail switch is OFF But in CYRS the described is that Tail LEDs will be ON whatever Tail switch is ON/OFF | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2024 | Ali | Req _ LED STRING ANIMATION_PO5_CYRS _ 003 _ v01 : Same note as previous point | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2025 | Ali | Requirements IDs shall have a diferent font different color and also version of the requirement shall be "-V01" not "_v01" | Accepted | Closed | Mali 30/1/2020: Point is reviewed and closed
24/1/2026 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed
30/1/2020 | Ali | Please provide all titles, tables and data with the same format of HSI also the requirement ID with a diff. suitable color | Accepted | Closed | Mali 6/2/2020: Pointstill open Mali 9/2/2020: Point is closed
30/1/2020 | Ali | Please remove curly brackets | Accepted | Closed | Mali 6/2/2020: Point is reviewed and closed
30/1/2020 | Ali | Edit the affected requirements by SIQ sheet | Accepted | Closed | Mali 6/2/2020: Point is reviewed and closed
2020-06-02 | Ali | Requirement "Req _ SEQUENCE OF TI FUNCTION RIGHT_PO5_CYRS_005-V01" & "Req _ SEQUENCE OF TI FUNCTION RIGHT_PO5_CYRS_006-V01", they don't declare that scenario of TI animation is repeated till TI switch is released. | Accepted | Closed | Mali 9/2/2020: Point is closed
2020-06-02 | Ali | Req _ SELECT WELCOME MODE_PO5_CYRS_001-V01 doesn't declare the switch is Mode switch it's just saying "If the switch" | Accepted | Closed | Mali 9/2/2020: Point is closed

## HSI review
Date | Reviewer | Review point | Acceptance | Point status | Comment
24/1/2026 | Ali | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Accepted | Closed | Mali 25/1/2020: Point is reviewed and closed