## Review
Date | Reviewer | Document | Review point | Point status | Comment
24/1/2020 | Ali | SIQ sheet | There are no questions in the SIQ sheet | Closed
24/1/2020 | Ali | LED String-CYRS | Project name shall be in the middle of first page not the table of contents | Closed | Mali 25/1/2020: Please remove "1.Project Name" no need for it
24/1/2020 | Ali | LED String-CYRS | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | LED String-CYRS | Block diagram isn't correct, it shall be a block has input signals(Tail signal - right TI signal - left TI signal - Mode signal) and has outputs (LEDs) | Closed
24/1/2022 | Ali | LED String-CYRS | Requirements section name is wrong, if you are reusing from another project please rename the section to be the name of our project LED string not speed control xD, any way this section's name shall be "Requirements description" | Closed | Mali 25/1/2020: Point is reviewed and closed
24/1/2022 | Ali | LED String-CYRS | Requirements are taken copy paste from CRS please provide the requirements with more details. Ex: Req_LED STRING ANIMATION_PO5_CYRS _ 001: describes the startup animation modes but at startup what will decide the running mode ? You should write a description of the signal/switch that decides the mode to be run, if you will implement this requirement you will run which mode? you will find your self asking about "what does make animation mode is mode 1 not 2?" | Closed
24/1/2023 | Ali | LED String-CYRS | Req _ LED STRING ANIMATION_PO5_CYRS _ 002 _ v01: Tail LEDs will be ON if Tail switch is ON and will be OFF if Tail switch is OFF But in CYRS the described is that Tail LEDs will be ON whatever Tail switch is ON/OFF | Closed
24/1/2024 | Ali | LED String-CYRS | Req _ LED STRING ANIMATION_PO5_CYRS _ 003 _ v01 : Same note as previous point | Closed
24/1/2025 | Ali | LED String-CYRS | Requirements IDs shall have a diferent font different color and also version of the requirement shall be "-V01" not "_v01" | Closed
24/1/2026 | Ali | LED String-HIS | Document status section shall be a table with the following coloms --> "Version, Date , Auther,Status " | Closed | Mali 25/1/2020: Point is reviewed and closed