## Sheet1
LED String Animation Project Plan [PO5_LSAN] |  |  | Team Lead: Youssef Kamal |  |  | Members: | Waleed Adel - Sara Abd ElRahman - Mennatullah Mostafa - Mohanad Sallam
Task | Description | ID | Assigned to | Assignation Date | Dead Line | Estimate Time | Actual Delivery Date | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Comments
CYRS_TASK001_V1 | Make Template to the CYRS document | TASK001 | Menna | 2020-01-21 | 2020-01-23 | 1h | 23/1/2020 | Revised | bar: Week1
SRS_TASK002_V1 | Make Template to the SRS document | TASK002 | Mohanad | 2020-01-21 | 23/01/2020 | 24h | 23/1/2020 | Revised | bar: Week1
HSI_TASK003_V1 | Make Template to the HSI document | TASK003 | Waleed | 2020-01-21 | 23/1/2020 | 24h | 23/1/2020 | Revised | bar: Week1
SIQ_TASK004_V1 | Make Template to the SIQ document | TASK004 | Sara | 2020-01-21 | 2020-01-24 | 48 h | 23/1/2020 | Revised | bar: Week1
CYRS_TO_SRS_TASK005_V1 | Break down Software requirments from CYRS to SRS requirments | TASK005 | Mohanad and Sara | 24/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised | bar: Week2
CYRS_TO_HSI_TASK006_V1 | Break down Hardware requirments from CYRS to HSI requirments | TASK006 | Walid and Menna | 24/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised | bar: Week2
REV_TO_CYRS_TASK007_V1 | Do the changes required in the review sheet to CYRS document | TASK007 | Menna | 25/1/2020 | 29/1/2020 | 24h | 29/1/2020 | Revised | bar: Week2
SIQ_Repair_TASK008_V1 | Remove questions asked by developer to developer. | TASK008 | Sara | 2020-03-02 | 2020-04-02 | 24h | 2020-03-02 | Revised | bar: Week3
CRS_ADD_ID_TASK009_V1 | Add ID to all three requirments in CRS requirments so we can track them in CYRS and HIS | TASK009 | Walid | 2020-03-02 | 2020-04-02 | 24h | 2020-04-02 | Revised | [7 empty] | Pushhed on 4/2 but done on 3/2 and had been commited | bar: Week3
MAKE_CLEAR_CRS_TASK010_V1 | Ask the costmer all the questiones that are mentioned in the meeting using the SIQ board (Can we use tri state flip switch in TI switch?, be more specefic in the welcome mode and the TI states, etc….) | TASK010 | Sara | 2020-03-02 | 2020-04-02 | 24h | 2020-03-02 | Revised | bar: Week3
MAKE_DESCRIPTION_TASK011_V1 | Make a good description to CYRS, HSI and SRS and use the same block diagram from HIS in all of them. Also remove all unused tiles like features in HIS. Also remove | TASK011 | Mohanad | 2020-03-02 | 2020-04-02 | 24h | 2020-04-02 | Revised | bar: Week3
CYRS_BREAKDOWN_TASK012_V1 | Break Down CRS to more than one CYRS requirment with more clear requirments. Also use the costmer answers from SIQ sheet. Also use the CRS requirment ID to track down the origin of each CYRS requirment. Also fix the versions in the history table. | TASK012 | Menna | 2020-04-02 | 2020-06-02 | 48h | 2020-06-02 | Revised | bar: Week3
HSI_ADD_REQ_ID_TASK013_V1 | Add ID to each HIS component. Also mention The ID from CRS that this component covers. Also add description to Hardware if needed. | TASK013 | Walid | 2020-04-02 | 2020-05-02 | 24h | 2020-05-02 | Revised | bar: Week3
SRS_REFORM_TASK014_V1 | Reforme SRS to match the new CYRS (Released). NB: Two Branches hase to be created by Team leader. | TASK014 | Sara and Mohanad | 2020-07-02 | 2020-08-02 | 24h | 2020-07-02 | Revised | bar: Week3
SIQ_AKNOWLAGE_TASK015_V1 | Read the new answers in the SIQ and aknowlage them | TASK015 | Sara | 2020-04-02 | 2020-04-02 | 12h | 2020-04-02 | Revised | bar: Week3
HSI_COVER_SIQ_TASK016_V1 | Cover all uncovered SIQ in HIS | TASK016 | Walid | 2020-05-02 | 2020-07-02 | 12h | 2020-07-02 | Revised | bar: Week3
BLOCK_DIAG_UPDATE_TASK017_V1 | Update CYRS and SRS with the block diagram from HIS document. This task should be done after finishing the SRS rightaway. | TASK017 | Sara | 2020-07-02 | 2020-07-02 | 12h | 2020-07-02 | Asseigned | bar: Week3
CYRS_6AND7_CHANGE_TASK018_V1 | Change CYRS to follow the review sheet | TASK018 | Menna | 2020-07-02 | 2020-07-02 | 12h | 2020-07-02 | Revised | bar: Week3
UPDATE_SRS_TASK019_V1 | Update SRS according to CYRS 6 and 7 | TASK019 | Mohanad | 2020-07-02 | 2020-07-02 | 12h | 2020-07-02 | Revised | bar: Week3
REARRANGE_CYRS_TASK020_V1 | Update CYRS arrangment so than status and document history before table of content. Also change the colour of the ID | TASK020 | Menna | 2020-08-02 | 2020-08-02 | 12h | 2020-08-02 | Revised | bar: Week4
HIS_TASK21_V1 | Update HIS with all the points mentioned in lecture. | TASK021 | Walid | 2020-08-02 | 2020-08-02 | 12h | 2020-08-02 | Revised | bar: Week4
SRS_TASK022_V1 | Update SRS according to the slides. | TASK022 | Sara and Mohanad | 2020-09-02 | 14/2/2020 | 6 days | 2020-12-02 | Revised | [7 empty] | Note the sara was occupies with the make hakathon. | bar: Week4
SRS_REV_TASK023_V1 | Update SRS acording to the review sheet. | TASK023 | Mohanad and Sara | 15/2/2020 | 19/2/2020 | 4 days | 16/2/2020 | Revised | bar: Week5
SRS_REV_TASK024_V2 | Update SRS sheet according to the open points in the review sheet. Please don’t close them by yourself. Also remove the HSl from the refrtence table. Also make a time line for the sequence in all modes. | TASK024 | Sara and Mohanad | 21/2/2020 | 22/2/2020 | 1 day | 21/2/2020 | Revised | bar: Week5
GDD_TASK025_V1 | Make basic structure of GDD | TASK025 | Walid | 21/2/2020 | 23/2/2020 | 2 days | 28/2/2020 | done | bar: Week5 to Week6
SRS_REV_TASK026_V1 | Start changing the SRS document according to review 11 to 15. | TASK026 | Sara and Mohanad | 25/2/2020 | 27/2/2020 | 2 days | 27/2/2020 | Revised | bar: Week6
GDD_TASK027_V1 | Make GDD file | TASK027 | Walid | 27/2/2020 | 28/2/2020 | 1 day | 28/2/2020 | done | bar: Week6
SRS_SW_CONT_TASK028_V1 | Change Software Context as defined in lecture. ie. Remove input feature and output feature and add stand alone switches and LED outputs. | TASK028 | Sara | 2020-03-01 | 2020-03-02 | 1 day |  | Revised | bar: Week7
GDD_TASK029_V1 | Make add software context in the firs page after the change in TASK028. add software feature with input feature, output feature and microcontroller feature. Add requirment ID to all public API's. change API table to input parameter and return. Add description to all input parameters. remove the description of how to implement the function. | TASK029 | Walid | 2020-03-01 | 2020-03-02 | 1 day |  | In progress | bar: Week7
CDD_TAIL_MOD_TASK030_V1 | Make CDD for TAIL Module | TASK030 | Menna | 2020-03-02 | 2020-03-05 | 3 days |  | Asseigned | bar: Week7
CDD_GPIO_MOD_TASK031_V1 | Make CDD for GPIO module | TASK031 | Youssef | 2020-03-02 | 2020-03-05 | 3 days |  | Asseigned | bar: Week7
|  | TASK032 | [5 empty] | Asseigned
|  | TASK033 | [5 empty] | Asseigned
|  | TASK034 | [5 empty] | Asseigned
|  | TASK035 | [5 empty] | Asseigned
|  | TASK036 | [5 empty] | Asseigned
|  | TASK037 | [5 empty] | Asseigned
|  | TASK038 | [5 empty] | Asseigned
|  | TASK039 | [5 empty] | Asseigned
|  | TASK040 | [5 empty] | Asseigned
|  | TASK041 | [5 empty] | Asseigned
|  | TASK042 | [5 empty] | Asseigned
|  | TASK043 | [5 empty] | Asseigned
|  | TASK044 | [5 empty] | Asseigned
|  | TASK045 | [5 empty] | Asseigned
|  | TASK046 | [5 empty] | Asseigned
|  | TASK047 | [5 empty] | Asseigned
|  | TASK048 | [5 empty] | Asseigned
|  | TASK049 | [5 empty] | Asseigned
|  | TASK050 | [5 empty] | Asseigned
|  | TASK051 | [5 empty] | Asseigned
|  | TASK052 | [5 empty] | Asseigned
|  | TASK053 | [5 empty] | Asseigned
|  | TASK054 | [5 empty] | Asseigned
|  | TASK055 | [5 empty] | Asseigned
|  | TASK056 | [5 empty] | Asseigned
|  | TASK057 | [5 empty] | Asseigned
TASK058