## HSI review
Date | Reviewer | Review point | Acceptance | Point status | Comment
2020-06-02 | Ali | Remove Team names (under project name) | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Update status to proposed as SRS is under review now | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Please provide a reference table to have "Doc. No, Ref. Doc. Name, Ref. doc. Status". | Accepted | Closed | Mali 13/2/2020: Point still open Mali 19/2/2020: Point is closed
2020-06-02 | Ali | Remove references section | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | Remove system features section | Accepted | Closed | Mali 13/2/2020: Point is closed
2020-06-02 | Ali | For every requirement, please provide a tacle like the one in presentation | Accepted | Closed | Mali 13/2/2020: Point is closed
13/2/2020 | Ali | From requirement SRS_003 till SRS_010: Under which conditions this sequence will be applied you should declare that this requirement is valid if it's mode 1 , shall the developer implement this requirement without knowing the condition to apply this animation or this animation will be applied without any entry condition! The CYRS requirement is clear and saying that if the switch is high SW shall apply mode 1. please make the requirement clear how these requirements has not input !!! the input indeed is mode value (mode 1 or mode 2). Also all these requirements shall be combined in one requirement as they represet the implementation of startup animation mode 1 | Accepted | Closed | Mali 19/2/2020: Point still open, as I said all requirements from 003 till 010 shall be combined you can't close the point by your self the reviewer shall take this decision not you,you can just accept or reject it Mali 24/2/200: Point is closed
13/2/2020 | Ali | Requirement SRS_011: Under which conditions this sequence will be applied you should declare that this requirement is valid if it's mode 2. Also the requirement shall declare that the animation scenario is repeated two times. | Accepted | Closed | Mali 24/2/200: Point is closed
13/2/2020 | Ali | Remove status and history from the first page, first page shall be the cover for the doc. | Accepted | Closed | Mali 13/2/2020: Point is closed
19/2/2020 | Ali | Please provide a context diagram as declared in the presentation | Accepted | Closed | Mali 13/2/2020: Point is closed
24/2/2020 | Ali | Date field in doc. History shall be the same format for all cells | Accepted | Open
24/2/2020 | Ali | Split the requirements to section, section for all TI reuirements, section for all Tail requirements and section for startup modes reuirements | Accepted | Open
24/2/2020 | Ali | There is no requirement to configure the HW pins according to HSI pin descreption | Accepted | Open
24/2/2020 | Ali | In Software context: - The inputs and outputs in the requirements shall be the same as output signals in sotware context for ex: in SRS_018 I shall see "Tail LEDs status" in the context instead it's not exist and all the rest signals like that - For the input side the signal for ex: "Mode signal" is input to "input feature block" and output from it at the same time ! | Accepted | Open